## Sheet2
Start | End | Task | Duration (days)
2025-09-22 | 2025-10-01 | Made a list of objectives, the project description and project title. | 10
2025-10-01 | 2025-10-08 | Created evaluation techniques for my objectives | 8
2025-10-08 | 2025-10-15 | Investigate package creation in Unity | 8
2025-10-02 | 2025-11-17 | Reading through papers | 16
2025-10-08 | 2025-11-17 | Finding more research papers | 10
2025-10-13 | 2025-10-22 | Working on the Dissertation Ethics Submission | 10
2025-10-16 | 2025-11-19 | Working on drafts of my Consent, PIS and Experiment documents. | 35
2025-10-28 | 2025-11-20 | Working on my D1 document | 24
2025-11-17 | 2025-11-19 | Working on my D2 video | 3

## Sheet1
Start | End | Task | Duration (days)
2025-09-22 | 2025-10-01 | Made a list of objectives, the project description and project title. | 9
2025-10-01 | 2025-10-08 | Created evaluation techniques for my objectives | 7
2025-10-08 | 2025-10-15 | Investigate package creation in Unity | 7
2025-10-02 | 2025-11-17 | Read through literature | 15
2025-10-08 | 2025-11-17 | Finding more research papers and other literature | 9
2025-10-13 | 2025-10-22 | Working on the Dissertation Ethics Submission | 9
2025-10-16 | 2025-11-19 | Working on drafts of Consent, PIS and Experiment documents. | 34
2025-10-28 | 2025-11-20 | Working on D1 document | 23
2025-11-17 | 2025-11-19 | Working on D2 video | 3
2025-11-01 | 2025-11-15 | Working on prototype scripts | 14
Start | End | Task | Duration (days)
2026-01-12 | 2026-01-25 | Coding example game 1 (no abstraction ver.) | 13
2026-01-12 | 2026-01-25 | Coding example game 2 (no abstraction ver.) | 13
2026-01-19 | 2026-01-29 | Coding example game 3 (no abstraction ver.) | 10
2026-01-12 | 2026-01-29 | Coding any extra programmes required for experiment | 17
2026-01-26 | 2026-02-01 | Setup & run pilot for experiment | 6
2026-02-02 | 2026-02-15 | Experiment recruitment & perform experiment | 13
2026-02-16 | 2026-02-20 | Analyse experiment results | 4
2026-02-02 | 2026-03-26 | Write up D3 report | 52
2026-02-21 | 2026-03-07 | Create Unity Package | 14
2026-03-08 | 2026-03-19 | Create example game 1 (abstraction ver.) | 11
2026-03-08 | 2026-03-19 | Create example game 2 (abstraction ver.) | 11
2026-03-12 | 2026-03-19 | Create example game 3 (abstraction ver.) | 7
2026-03-20 | 2026-03-26 | Analyse example games' abstraction | 6
Start | End | Task | Duration (days)
2026-01-12 | 2026-01-25 | Coding examples game 1 with no abstraction | 14
2026-01-12 | 2026-01-25 | Coding examples game 2 with no abstraction | 14
2026-01-19 | 2026-01-29 | Coding example game 3 with no abstraction | 11
2026-01-12 | 2026-01-29 | Coding any extra programmes I will use as examples in my experiment | 18
2026-01-26 | 2026-02-01 | Setup and run pilot for experiment | 7
2026-02-02 | 2026-02-15 | Recruit for and perform experiment | 14
2026-02-16 | 2026-02-20 | Analyse my experiment data and make requirements for my package based on the results | 5
2026-02-02 | 2026-03-26 | Write up D3 report | 53
2026-02-21 | 2026-03-07 | Create my unity package based on my analysis | 15
2026-03-08 | 2026-03-19 | Create a new version of game 1 by replacing the code with methods from my package | 12
2026-03-08 | 2026-03-19 | Create a new version of game 2 by replacing the code with methods from my package | 12
2026-03-12 | 2026-03-19 | Create a new version of game 3 by replacing the code with methods from my package | 8
2026-03-20 | 2026-03-26 | Analyse within my D3 the resulting example games created using my package and how my package benefitted the code. | 7